# KNCC Material Procurement, Inventory & VPO Management System

Combined Business Requirements, Workflow Documentation and Reporting Requirements

# 1. Business Overview

KNCC currently manages material procurement, inventory tracking, vendor invoices, purchase orders, change orders and VPO reporting through Excel-based processes. The workflow has been developed around real project requirements from Willow Way Apartments and Cobia Cove. The primary goal is to maintain visibility of approved quantities, deliveries, inventory balances and material costs throughout the project lifecycle.

# 2. Project References

Business rules and reporting requirements documented here are based primarily on Willow Way Apartments and Cobia Cove. These projects utilize vendor proposals, purchase orders, change orders, invoices, delivery tracking and VPO reporting to manage framing lumber, engineered wood products, panels, siding, house wrap and miscellaneous materials.

# 3. Material Categories

Lumber: Dimensional lumber(Types : PT or MCA same, SYP #2, SYP #3 etc..)  and (pressure-treated(PT) lumber=MCA).
LVL / PSL / GLB / EWP: Engineered framing products.
Panels: ZIP sheathing, OSB, plywood, gypsum panels and treated panels.
Each Items: Adhesives, flashing, sill sealers, tape, fasteners and miscellaneous construction materials.
Siding and House Wrap: For reporting and inventory purposes these materials shall be tracked under the Each category.

# 4. Procurement Workflow

Estimate → Material Planning → Vendor Proposal → Purchase Order Approval → Change Orders → Deliveries → Vendor Invoices → Inventory Updates → VPO Reporting → Variance Monitoring.

The process begins with approved material quantities. Vendors provide proposals and pricing. Approved quantities are issued through Purchase Orders. Any modifications are documented through Change Orders. Deliveries and invoices are recorded and inventory balances are updated accordingly.

# 5. VPO Report Requirements

The Variance Purchase Order (VPO) report is the primary management report. The report shall contain Project Name, Vendor Name, Material Category, Material Description, Dimensions, CO Quantity, Variance Quantity, Unit Cost, Extended Cost.

# 6. Inventory Management

Delivered quantities increase inventory balances. Material issued to the field reduces inventory balances. Historical transactions shall remain available for auditing and reconciliation. Inventory reports shall identify shortages, excess inventory, open commitments and quantity variances.

# 7. Business Formulas

Linear Feet (LF) = Pieces(PC) × Length(L)
Board Feet (BF) = (Thickness(T) × Width(W) × Length × Pieces) ÷ 12
Panel Square Feet (SF) = Pieces × Width × Length
Approved Quantity = PO Quantity + Approved Change Order Quantity
Delivery Percentage = Delivered Quantity ÷ Approved Quantity × 100
Inventory Balance = Delivered Quantity − Issued Quantity
Variance Quantity = Approved Quantity − Delivered Quantity
Cost Variance % = (Actual Cost − Estimated Cost) ÷ Estimated Cost × 100
Change Order Impact % = Change Order Value ÷ Original Purchase Order Value × 100

# 8. Change Order Management

Approved Change Orders modify the original Purchase Order quantities. The VPO report must always reflect the latest approved quantities. Material substitutions, quantity additions and quantity reductions shall be documented through approved change orders before affecting inventory or reporting.

# 9. Invoice Management

Vendor invoices are matched against approved project quantities. Multiple invoices may be associated with a single material item. Delivered quantities accumulate across all invoices and deliveries. Invoice records shall remain linked to the corresponding project, vendor and material line item.

# 10. Dashboard Requirements

Procurement Dashboard: PO values, CO values and outstanding commitments.
Inventory Dashboard: Inventory on hand, shortages and excess inventory.
Financial Dashboard: Material budgets, actual costs and variances.